## Receipts
Date | Receipt ID | Source | Description | Category | Amount | Method | Status
2025-01-05 | REC-001 | Client Deposit | Initial Booking Token | Deposit | 2500000 | Cheque | Received
2025-02-01 | REC-002 | Bank Al-Habib | Construction Loan Tranche 1 | Loan Draw | 5000000 | Bank Transfer | Received
2025-03-15 | REC-003 | Client Payment | Milestone: Plinth Level | Progress Payment | 3500000 | Cheque | Received
2025-04-10 | REC-004 | Bank Al-Habib | Construction Loan Tranche 2 | Loan Draw | 4500000 | Bank Transfer | Received
2025-05-20 | REC-005 | Client Payment | Milestone: Grey Structure | Progress Payment | 3000000 | Online Transfer | Pending

## Payments
Date | Payment ID | Vendor | Description | Category | Amount | Method | Status
2025-01-10 | EXP-101 | RDA | Map Approval & NOC | Permits | 150000 | Pay Order | Paid
2025-01-15 | EXP-102 | Jamil Excavators | Plot Leveling & Excavation | Site Prep | 450000 | Cash | Paid
2025-01-25 | EXP-103 | Bestway Cement | Cement (400 Bags) | Materials | 480000 | Invoice | Paid
2025-02-02 | EXP-104 | Amreli Steels | Steel Rebar (5 Tons) | Materials | 1350000 | Cheque | Paid
2025-02-10 | EXP-105 | Labor Contractor | Labor - Foundation Work | Labor | 850000 | Cash | Paid
2025-02-20 | EXP-106 | Local Sand Supplier | Sand & Crush (20 Dumpers) | Materials | 600000 | Cash | Paid
2025-03-05 | EXP-107 | Bricks Company | A-Class Bricks (50,000) | Materials | 750000 | Cheque | Paid
2025-03-15 | EXP-108 | Labor Contractor | Labor - Brickwork (1st Floor) | Labor | 900000 | Cash | Paid
2025-03-25 | EXP-109 | Pak Cables | Electrical Piping & Boxes | Subcontractor | 350000 | Invoice | Paid
2025-04-05 | EXP-110 | Master Sanitary | Plumbing Rough-in | Subcontractor | 420000 | Cheque | Pending
2025-04-15 | EXP-111 | Rental Services | Shuttering & Scaffolding | Equipment | 250000 | Cash | Paid
2025-04-20 | EXP-112 | Site Security | Guard Salary (3 Months) | Overhead | 90000 | Cash | Paid

## Summary
Project Dashboard: Skyline Heights - Phase 1 (Rawalpindi)
Total Inflow (Receipts) | Total Outflow (Payments) | Net Cash Balance
18500000 | 6640000 | 11860000
Budget vs Actual Breakdown
Category | Budget (PKR) | Actual (PKR) | Variance
Materials | 4000000 | 3180000 | 820000
Labor | 2000000 | 1750000 | 250000
Subcontractor | 1000000 | 770000 | 230000
Site Prep | 500000 | 450000 | 50000
Equipment | 300000 | 250000 | 50000
Permits | 200000 | 150000 | 50000
Overhead | 150000 | 90000 | 60000
TOTAL | 8150000 | 6640000 | 1510000